**Alvington NDP Meeting Minutes - 16th January 2017**

|  |  |
| --- | --- |
| **Attendees**: |  |
| Kate BOUGH (GRCC) | Alan HASLAM |
| Gary COLLIER | Alec DAVIS |
| Eric ROBSON | Larine GEORGE |
|  |  |

**Apologies:** Tony ISMAY, John WOOD, Margaret HARRIS and Verlie EAGLES

***Copy***:

**Meeting Location**: Alvington Village Hall, Glos. **Start**: 13:30 pm **Finish**: 15:00 pm

**Objective**: Review Open Day Consult Summary detail, gaps in consultation, next steps and the new budget.

**Next Meeting: Monday 6th February 2017, at 13:30 Village hall.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Item** | **Actions** | **Who** | **Date Raised** | **O/L Complete** |
| 1. | Appraisal Areas (for reference), Parish split into eight (8) areas.  ***Area 1 North ~ Glebe Farm, Rookery Wood & Lower Common***  ***Area 2 North West ~ Clanna Estate & Wood***  ***Area 3 North East ~ Lydney Park Estate ~ Meend Plantation***  ***Area 4 North West ~ Barnage & Pipers Meadow***  ***Area 5 North of A48 ~ Duncastle and Garlands Road areas***  ***Area 6 North of A48 ~ Nupend and Park Farm areas***  ***Area 7 South of A48 Main Road – River side***  ***Area 8 South East of A48 Main Road ~ Playing field***    ***Appraisal Areas.***  Must be kept separate and very important character assessments.  Material Evidence for planning applications.  Good quality photos required very important may need retake in the spring.  One or two persons converge above areas, standard format then resubmit to steering group for review. Join together and flow examiners like feel.    Added information allowed and updates to appraisals. To be ready for the NDP March 2017 Meeting | John W/Alan H  Susanne J/Ann T  Gary C  John W/Alan H  Gary C  Gary C  Tony I /Alec D  Gary C      Statement  Kate B  ALL    Alan H    Kate B    ALL | 27th June  27th June  27th June  27th June  27th June  27th June  27th June  27th June      16th Jan  16th Jan  16th Jan  16th Jan    16th Jan  16th Jan      16th Jan | 22nd Oct |
| 2. | Themes. Evidence presented at OPEN day on 23rd October 2016  ***Traffic and Road Safety***  ***Infrastructure*** – also to contain open day survey results  ***Facilities*** – also to contain open day survey results  ***Services***  ***Character and Housing – FDDC report***  ***Polices and Standards***  ***Transport***  ***Employment and Economy***  ***Environment***    ***Themes.***  Priorities. May need modifying, visions from consultations, refer to Event analysis (see attached) | ~~Gary C~~ Verlie E  Dan P  Dan P  Dan P  John W  Dan P  Verlie E  Dan P  Gary C      Kate B | 23rd May  23rd May  16th Jan  16th Jan  23rd May  23rd May  23rd May  23rd May  23rd May      16th Jan | 22nd Oct        22nd Oct |
| 3. | **Parish Church**  Any old photos available.  Contact Claris Church Warden | Statement Tony I. | 17th Oct  17th Oct |  |
| 4. | **Open Green Spaces. Identify.**  List in NDP  Once designated cannot be built on.  Forest waste – open green space.  Aspect views, which do you value. | Statement ALL  Statement  ALL | 17th Oct  17th Oct  17th Oct  17th Oct |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | ***Open Spaces****.*  List must be generated. Everyone on Steering Group to list places.  Clearly identify open space areas on Maps.  Village Green outside Globe Inn, one example.  Garlands Road, two areas protected spaces, if council designate, village, may not agree, highlight designated green spaces, size etc, ownership.  Clanna Ponds Forest waste? Protected?  Forestry Commission – designation mark all areas on maps in the Alvington Parish. Email evidence required. | ALL  ALL  Statement        Eric ROBSON | 16th Jan  16th Jan  16th Jan        16th Jan |  |
| 5. | **Photos**  Old Photos depicting village history to be sourced for future events. | ALL | 17th Oct | Ongoing |
| 6. |  |  |  |  |
| 7. | **OPEN day feedback.**  109 attendees. 80 questionnaires completed. Displays complemented. Maps generated considerable interest, noted Clanna Lane NOT Clanna Road on all historical maps displayed. Broadband and mobile phone coverage were the major infrastructure comment.    Age groups 12 – 17 and 18 – 25 little attendance or feedback. Why?  Demographics local clubs, schools.  Does the number of attendees in these groups reflect demographics?    Reviewed data on draft two (2) pages presented. FOOTPATHS poor.  FOOTPATHS Accessibility, require breaking out into more detail.  Use attached Event Analysis.  Pavements hard surfaces  Footpaths and gates. Identify where issues are observed, on a Map. Cycle Paths  Bridle Ways  Old Road Footpath Alvington to Alyburton.    ADD **Event Analysis** to Web Site    Additional Analysis required developing plan.    “Consult survey results” **summary** to be uploaded to WEB SITE upon receipt and in next village Newsletter.  Social interaction noted, all very good.  Review gaps in Post codes to improve future OPEN day attendance.    Clanna Lane (on maps) or Clanna Road needs clarifying with FDDC.    Update budget (see attached). Review at next meeting.  Latest Budget reviewed and accepted.  Updated spend to be obtained from Parish Clerk.  Updated budget with above input to be reviewed at next meeting. | Statement    ALL    John WOOD    ALL  ALL  ALL  ALL  ALL  ALL  ALL  ALL    Gary C    Kate B      Gary C    ALL        Kate B/Emma M Kate B  Kate B/Emma M  Kate B/Emma M | 16th Nov    16th Nov    16th Jan    16th Nov  16th Jan  16th Jan  16th Jan  16th Jan  16th Jan  16th Jan  16th Jan    16th Jan    16th Nov      16th Nov    16th Nov    16th Jan    16th Nov  16th Jan  16th Jan  16th Jan | Ongoing        Complete                      15th Dec          Ongoing        15th Dec  CLOSED |
| 8. | **BUSINESS survey template.**  To be produced.    Once provided by Kate B. up load to WEB SITE. Could then be downloaded to submit.    Business survey draft reviewed, new updated version to be circulated Post meeting. Updated survey circulated to steering group.  Question. Consider HOW TO identify and circulate ALL businesses big or small in Parish MUST be decided at next Meeting.    Obtain views of businesses, Farmers and any proposed diversification plans for the future.    Meet Forest of Dean District Council Planners in New Year with draft conformity. | Kate B    Gary C  Gary C    Kate B  Kate B  ALL      ALL      Kate B | 16th Nov    ~~16~~~~th~~ ~~Nov~~  16th Jan    16th Jan  16th Jan  16th Jan      16th Nov      16th Nov | 1st Dec          16th Jan  CLOSED |
| 9. | **NDP Project Plan.**  Kate B to mail Gary C. an updated plan for circulation. | Kate B | 16th Nov |  |
|  | Updated Project Plan to be up loaded to WEB SITE. | Gary C | 16th Nov |  |
| 10 | .**Next OPEN Event.**  Draft polices evidence to match.  Flooding identify on Map. Hard evidence Photos. Housing what if any additional clearly identify.    Without support of villagers, difficult to progress through planning.    Farmers for example, any plans for Farm Shops, Golf course etc.    Parking for any developments. Negotiation required. | Statement ALL  ALL    Statement    ALL    ALL | 16th Nov  16th Nov  16th Nov    16th Nov    16th Nov    16th Nov |  |
| 11 | .**Next STEPS.**  *Businesses*, any proposed plans to be identified and listed.    *Clubs*, Football, Cricket, Dog Training, List to be developed.    *Community Facilities*,  Village Hall, who uses, what age groups and how many. Sports Facilities, who uses, frequency, what age groups & how many. | ALL    ALL      Verlie E/Gail T    Gary C | 16th Nov    16th Nov      16th Nov    16th Nov |  |
| 12 | .**Character Appraisal Areas Assessments** (see item 1 for list) Require pulling together. As presented used different formats.    Take best and standardise all appraisal areas ideally two (2) persons    Cut and Paste readable and concise.    Appraisals must reflect feel of Parish. | Statement        Statement    Statement | 16th Nov    16th Nov    16th Nov    16th Nov | See Item 1    See Item 1    See Item 1    See Item 1 |
| 13 | .**FDDC requires**.  Habitats screening Policies Map of Parish, Glos Wild Life Trust.  Sites of Special Interest, to be identified.  Erosions, banks River Severn. Maps and rate of erosions | Gary C | 16th Nov  16th Nov  16th Nov |  |
| 14 | .**AOB**  Open Day Consultation Summary (previously circulated) see page 2. What you like What to improve.  House Prices  Severn Bridge Tolls  Environment  Tranquil location  Small service village  Accessibility    Heritage sites and buildings even if not listed – Complete list to be drafted. I.e. Old Parsonage, Mikla Bridge & Swan Hill Pac bridge.    Vision inside and outside village, for next open day.    Date of next NDP meeting – **Monday 6th February 2017** | ALL  ALL                Verlie E      ALL    Statement | 16th Jan  16th Jan                16th Jan      16th Jan    16th Jan | 16th Jan |

***Attachments:***

* Alvington NDP Event Analysis (Open Day Results) ~ 23 October 2016
* Alvington BUSINESS survey – questionnaire ~ 16th January 2017
* Alvington Communication Strategy ~ April 2016

***Copy:*** File